## issues
Date | Issues (Single issue per row) | Status | Description | Assignee | Confirmed By | Reported By
2022-07-08 | Expoloader-Signup: able to signup without ticking the I agree check box |  |  | rilfi@expoloader.com
2022-07-19 | Some SKUs repeated multiple times |  | In container and SKU fields have stored same data in multiple times. | rilfi@inoovalab.org
2022-07-19 | Some containers repeated multiple times
2022-07-19 | Unable to select different SKUs in automation | RESOLVED | use correct locators | ajmalhinas@gmail.com
2022-07-27 | Unable to select different loading type in automation | RESOLVED
2022-07-28 | Unable to use different xpath,attributes
2022-07-30 | combo boxes are case sensitive
2022-07-30 | in combo scroll is hiding automatically. Unable to scroll by mouse
2022-08-02 | in new Expoloader account has no container data
2022-08-03 | After reloading the expoloader page data container has no data, we need to logout and again log in
2022-08-04 | in pallet loading,when i delete the multi SKU pallet, the select sku input field is not disabled and selecting SKU makes the app stuck |  | Steps to reproduce: isPalletLoading |  | ajmalhinas@gmail.com | Mohammed Hazeem
2022-08-04 | in pallet loading, it allow to delete the multi SKU pallet,when loading the SKU |  |  |  |  | Mohammed Hazeem
2022-08-05 | it allow to click the reset button while SKU loading
2022-07-09 | Using icon instead of button in sku management page crud
2022-09-07 | Error message is being displayed under header and cannot see the error message in sku management |  |  | rilfi@expoloader.com |  | Sasitharan
2022-09-07 | Cannot select floor loading container and pallete loading container |  |  | rilfi@expoloader.com |  | Sasitharan